SUBJECT CODE: MTH601

Assignment # 01 Spring 2019

Note: Please Check it twice by yourself and also make some changes, Don’t make exact copy paste technique otherwise you will get mark 0 (zero) if you make same copy.

Solution:

- Construct the table which shows the relationship

| Activities | Predecessor |
| --- | --- |
| A | - |
| B | A |
| C | - |
| D | C |
| E | B |
| F | D, E |
| G | F |

- Calculate the following

  - Earliest Start Time

  - Earliest Finish Time

  - Latest Start Time

  - Latest Finish Time

Answer:

| Activity | Earliest Start Time | Earliest Finish Time | Latest Start Time | Latest Finish Time |
| --- | --- | --- | --- | --- |
| A | 0 | 4 | 0 | 4 |
| B | 4 | 11 | 4 | 11 |
| C | 0 | 6 | 6 | 12 |
| D | 6 | 11 | 13 | 18 |
| E | 11 | 18 | 11 | 18 |
| F | 18 | 24 | 18 | 24 |
| G | 24 | 29 | 24 | 29 |

- Calculate the total float of each activity

Answer: Float = Latest Finish Time – Earliest Finish Time

| Activity | Float |
| --- | --- |
| A | 0 |
| B | 0 |
| C | 6 |
| D | 7 |
| E | 0 |
| F | 0 |
| G | 0 |

- Critical Path

There are 2 Paths

A+B+E+F+G = 4 +7 + 7 +6+5 = 29

C+D+F+G=6+5+6+5 =22

A+B+E+F+G longest Path hence it is critical path 29

- Project Completion Time is 29 Days